## Project schedule
| TESIS | [5 empty] | Project start: | [7 empty] | 2025-09-01
| ITB | Project lead |  |  |  |  | Display week: | [7 empty] | 1
Judul: PENGEMBANGAN SISTEM REKOMENDASI ADAPTIF REAL-TIME UNTUK DESTINASI WISATA: OPTIMALISASI KEBERAGAMAN DAN CAKUPAN GUNA MENDORONG PEMERATAAN DISTRIBUSI PARIWISATA
[7 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-09-01 to 2025-12-14
 | time axis 2025-09-01 to 2025-12-14
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
1.0 Fase 1: Perencanaan dan Finalisasi Metodologi (1 September - 14 September 2025)
| 1.1 Finalisasi Studi Literatur (1 September - 10 September 2025): | MAHASISWA | 0% | 2025-09-01 | 2025-09-10 | 10
| 1.1.1 Pendalaman literatur terkait metrik keberagaman (diversity) dan cakupan (coverage) | MAHASISWA | 0% | 2025-09-01 | 2025-09-05 | 5
| 1.1.2 Studi algoritma re-ranking seperti Maximal Marginal Relevance(MMR) | MAHASISWA | 0% | 2025-09-03 | 2025-09-07 | 5
| 1.1.3 Finalisasi tinjauan pustaka untuk Bab 2 | MAHASISWA | 0% | 2025-09-08 | 2025-09-10 | 3
| 1.2 Perancangan Arsitektur Sistem Final (1 - 14 September 2025): | MAHASISWA | 0% | 2025-09-01 | 2025-09-14 | 14
| 1.2.1 Pemetaan alur data real-time (misal: interaksi pengguna) untuk adaptasi model | MAHASISWA | 0% | 2025-09-02 | 2025-09-10
| 1.2.2 Desain final skema database untuk menampung data log interaksi | MAHASISWA | 0% | 2025-09-08 | 2025-09-14
| 1.3 Penyiapan Data dan Lingkungan (1 - 14 September 2025): | MAHASISWA | 0% | 2025-09-01 | 2025-09-14
| 1.3.1 Pengumpulan dataset awal (jika ada tambahan dari yang sudah ada) | MAHASISWA | 0% | 2025-09-01 | 2025-09-07
| 1.3.2 Finalisasi dan verifikasi lingkungan pengembangan (Docker, Python, React) | MAHASISWA | 0% | 2025-09-08 | 2025-09-14
2.0 Fase 2: Pengembangan dan Implementasi Sistem (8 September - 19 Oktober 2025)
| 2.1 Pengembangan Backend (Fokus Utama) (8 September - 19 Oktober 2025): | MAHASISWA | 50% | 2025-09-08 | 2025-10-19 | 42
| 2.1.1 Implementasi Pengambilan Data Real-time | MAHASISWA | 50% | 2025-09-08 | 2025-09-21 | 14
| 2.1.2 Implementasi Algoritma Keberagaman dan Cakupan | MAHASISWA | 50% | 2025-09-15 | 2025-10-05 | 21
| 2.1.3 Implementasi Logika Adaptif |  | 50% | 2025-09-22 | 2025-10-12
| 2.1.4 Refinement API |  | 50% | 2025-10-06 | 2025-10-19
| 2.1.5 Pengujian Unit dan Integrasi Backend |  | 50% | 2025-10-13 | 2025-10-19
| 2.2 Pengembangan Frontend (22 September - 19 Oktober 2025): |  | 50% | 2025-09-22 | 2025-10-19
| 2.2.1 Desain Antarmuka (UI/UX) |  | 50% | 2025-09-22 | 2025-09-28
| 2.2.2 Implementasi komponen UI untuk interaksi pengguna | MAHASISWA | 50% | 2025-09-29 | 2025-10-12 | 14
| 2.2.3 Integrasi Frontend dengan API Backend |  | 50% | 2025-10-06 | 2025-10-19
| 2.2.4 Pengujian fungsionalitas di sisi klien |  | 50% | 2025-10-13 | 2025-10-19
3.0 Fase 3: Eksperimen dan Evaluasi (13 Oktober - 16 November 2025)
| 3.1 Perancangan Skenario Eksperimen (13 - 26 Oktober 2025): | MAHASISWA | 50% | 2025-10-13 | 2025-10-26 | 14
| 3.1.1 Menentukan metrik evaluasi |  | 50% | 2025-10-13 | 2025-10-19
| 3.1.2 Merancang skenario perbandingan |  | 50% | 2025-10-20 | 2025-10-26
| 3.2 Pelaksanaan Eksperimen (20 Oktober - 9 November 2025): |  | 50% | 2025-10-20 | 2025-11-09
| 3.2.1 Menjalankan simulasi atau pengujian dengan pengguna |  | 50% | 2025-10-20 | 2025-11-02
| 3.2.2 Mengumpulkan data hasil eksperimen dari log sistem |  | 50% | 2025-10-27 | 2025-11-09
| 3.3 Analisis Hasil (27 Oktober - 16 November 2025): |  | 50% | 2025-10-27 | 2025-11-16
| 3.3.1 Mengolah dan menganalisis data hasil eksperimen |  | 50% | 2025-10-27 | 2025-11-09
| 3.3.2 Membandingkan hasil antar skenario dan menarik kesimpulan awal |  | 50% | 2025-11-10 | 2025-11-16
4.0 Fase 4: Penulisan Tesis dan Finalisasi (15 September - 30 November 2025)
| 4.1 Penulisan Konten Tesis (dilakukan paralel) (15 September - 23 November 2025): | MAHASISWA | 25% | 2025-09-15 | 2025-11-23 | 70
| 4.1.1 Penulisan Bab 1 (Pendahuluan) & Bab 2 (Tinjauan Pustaka) | MAHASISWA | 25% | 2025-09-15 | 2025-09-28 | 14
| 4.1.2 Penulisan Bab 3 (Metodologi Penelitian) |  | 25% | 2025-09-29 | 2025-10-12
| 4.1.3 Penulisan Bab 4 (Implementasi dan Hasil Eksperimen) |  | 25% | 2025-10-13 | 2025-11-09
| 4.1.4 Penulisan Bab 5 (Kesimpulan dan Saran) |  | 25% | 2025-11-10 | 2025-11-23
| 4.2 Revisi dan Bimbingan (Periodik selama 1 September - 30 November 2025): |  | 25% | 2025-09-01 | 2025-11-30
| 4.2.1 Bimbingan rutin dengan dosen pembimbing. |  | 25% | 2025-09-01 | 2025-11-30
| 4.2.2 Revisi naskah tesis berdasarkan masukan. |  | 25% | 2025-09-01 | 2025-11-30
| 4.3 Persiapan Sidang (10 - 30 November 2025): |  | 25% | 2025-11-10 | 2025-11-30
| 4.3.1 Finalisasi naskah dan dokumen persyaratan |  | 25% | 2025-11-10 | 2025-11-23
| 4.3.2 Pembuatan materi presentasi sidang |  | 25% | 2025-11-17 | 2025-11-26
| 4.3.3 Pendaftaran sidang tesis |  | 25% | 2025-11-27 | 2025-11-30
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.